CRITICAL PATH METHOD
====================
(or cpm of another kind)

The  Critical Path Method is a project management tool aimed at  presenting 
any  task as a series of activities,  listed in order of dependance and  in 
such  a way that the activity path requiring the least time for  completion 
(known as the Critical Path) can be identified and managed more closely.

Usually,  people  tend to cooperate better and become less frustrated  with 
the  project  when  it  is reasonably well  planned,  and  everyone  has  a 
reasonable idea of what they are expected to contribute,  when, and for how 
long.

The Critical Path Method may be as simple as a primitive network (or arrow) 
diagram on the back of an envelope, to a sophisticated computer based model 
with  thousands  of  activities and dependancies taking  into  account  the 
scheduling of available resources for the work.

The arrow diagram
-----------------

The task is represented as an 'arrow diagram'. Each activity is represented 
by an arrow;  the beginning and end of each activity (arrow) is marked with 
a circle called a node and which contains a reference number.

Say we have the start of activity B dependant on the completion of activity 
A.  The head of the arrow for A terminates in a circle (or node) identified 
with a number - let us say 32. The head of activity A terminates at node 32 
and  the  tail  of activity B starts from node 32.  Say now  that  we  have 
another activity,  C, which may start from the same node as A - say node 31 
- and is required to be completed at the same time as B, at node 34.

Activity  C goes direct from node 31 to 34 while activities A and B go from 
31 to 32, and 32 to 34 respectively.

If  we  put some times on the activities we start to get a picture  of  the 
task.

activity     nodes   estimated time
   A         31-32        1hr
   B         32-34        3hr
   C         31-34        5hr

Easily,  activity C is going to take 5hrs and the sum of activities A and C 
will take (1+3) or 4hrs.

Suppose now that we have another activity,  D,  which goes directly from 31 
to 34. The table would look like:

activity     nodes   estimated time
   A         31-32        1hr
   B         32-34        3hr
   C         31-34        5hr
   D         31-34        2hr

The numbering of the nodes does not allow the activity or activity time  to 
be identified correctly.  The solution is to include a 'dummy' activity, of 
zero time and indicated by a dotted arrow, together with another node - say 
33.

activity     nodes   estimated time
   A         31-32        1hr
   B         32-34        3hr
   C         31-34        5hr
   D         31-33        2hr
   E         33-34      dummy - zero time 

Now there is no clash.  Note that it is more logical to use numbers for the 
nodes  in  a way that the higher number always appears at the head  of  the 
arrow. This makes it easier for a computer to know which way we are heading 
- even if we dont!.

The Critical Path
-----------------

There are three routes from 31 to 34:
                A    1hr             B    3hr            (total time 4hr)
         31 ----------------> 32 -----------------> 34 
        0/                   1/                    5/ 
                D    2hr           E   0hr dummy          (total time 2hr)
         31 ----------------> 33 .................> 34
        0/                   2/                    5/
                C    5hr                                  (total time 5hr)
         31 --------------------------------------> 34
        0/                                         5/

The numbers given under each of the nodes is the earliest time at which the 
next activity can start (EST).  Note that at activity 34 the earliest start 
time for the next activity is 5, because all activities must be finished at 
34 before activity 34-35 (F) can commence. This means that activities A,B,D 
and E will have spare time (known as 'float'). 

Activity C will have no float and is known as the 'critical path'.

Project times
-------------

Ideally,  the  objective  is  to  manage resources so that  every  path  is 
critical, and the overall time of the project can be minimized.

If  now  we work backwards from node 34 we will get a second  figure  which 
will indicate the 'latest finish time' (LFT),  the time beyond which   that 
path will become critical.

Several of these times may be computed:
          EST  earliest start  time for the activity
          EFT  earliest finish time for the activity
          LST  latest   start  time for the activity
          LFT  latest   finish time for the activity
          float, or that free time between the earliest and latest possible 
          finish times for the activity. 

The diagram now looks like this:

                A    1hr             B    3hr            (total time 4hr)
         31 ----------------> 32 -----------------> 34    total float 1h
        0/1                  1/2                   5/5
                D    2hr           E   0hr dummy          (total time 2hr)
         31 ----------------> 33 .................> 34     total float 3h
        0/3                  2/5                   5/5
                C    5hr                                  (total time 5hr)
         31 **************************************> 34      * critical *
      * 0/0                                        5/5


Yes, BUT.........

Some  will argue about activity times,  and about the value of using such a 
method.  Usually, people of some experience will have a pretty good idea of 
how long it takes to do a job - but they are more likely to express it as a 
range  of times 'anywhere between one and three hours ...'.  These are  the 
most optimistic (1) and most pessimistic (3) times respectively. If pressed 
to it for a realistic average,  we might get '2.5 hours' (.... 'but it wont 
work anyway ' ....)

To  get  a reasonable estimated time for the  diagram,  use  the  following 
formula:

                      most optimistic + 4*most realistic + most pessimistic
     estimated time = -----------------------------------------------------
                                                6
In our case we have an estimated time of (1+4*2.5+3)/6 = 2.33h

The Program
-----------

The  program (critpath.mwb) was written in Microworld BASIC,  and  modified 
countless times - first from a cassette storage system;  ultimately to suit 
my 128k dual drive MicroBee.

This version is made available to  the  public domain.

I  have no doubt that if someone has the need they will revise it and  tidy 
it up. 

Example
-------

The example below is that of erecting a tent, not that anyone is interested 
in the management of tent erection unless it is pouring with rain;  but  it 
could  apply  equally  well to the overhaul of a diesel engine  or  to  the 
building of a house. 





Erecting a Tent
---------------

Start by listing all the activites required to do the job just as they come 
to mind. Dont try to put them in order just yet. Then draw an arrow diagram 
(on  a  piece of butchers paper with a felt pen is ideal) but  without  the 
nodes numbered. Just aim at getting the dependance of each activity right. 

If  you run the little program ARROW.MWB it will show roughly how a network 
diagram connects the nodes. You will get a better idea if you draw a proper 
one  on graph paper using circles at the nodes,  arrow heads at the end  of 
each  activity,  numbers to identify each node and letters to identify  the 
activities.

You might like to change several of the activities through the 'alter data' 
option  at  the  menu to investigate the effect.  Pay no attention  to  the 
number  of parallel paths until you have drawn the first diagram  and  find 
your  resource  limitations.  Then you can modify the diagram to  have  the 
number of paths your resources will allow.

When  you have the diagram dependancies correct,  number the nodes  from  0 
upwards. Make sure that the higher numbers always appear at the arrowheads.

Only  when you have done this should you start to enter times,  and this is 
the time to use the program (CRITPATH.MWB)

 activity     nodes      est time   description
               start finish    mins

        1	0	1	10.	find suitable site 
 	2	1	4	15.	clear stones away
 	3	3	4	 0.	DUMMY
 	4	1	3	12.	level the site
 	5	1	2	 5.	get tent from car
 	6	2	4	 0.	DUMMY
 	7	4	5	 3.	unpack tent
 	8	4	7	 5.	unpack pegs & poles
 	9	5	6	 7.	lay out groundsheet
 	10	6	7	10.	lay out tent base 
 	11	7	9	 5.	peg out gndsht/base
 	12	8	9	 7.	peg out tent/guys
 	13	7	8	 2.	erect poles
 	14	9	11	 3.	tighten tent guys
 	15	8	10	 4.	fit fly to tent
 	16	10	11	 2.	tighten fly guys
 	17	11	12	20.	celebrate!

At  the opening menu you will have the choice of entering the data manually 
(option  0)  or  of  calling it up from disk.  Data  for  this  example  is 
contained in file TENT.DAT or TENT1.DAT. It can be loaded using option 7.

Two  data  files are included because the program will sort the  file  into 
order.  If you attempt to save it using option 6, the original data will be 
replaced with the sorted data.


Selection  of option 1 (List schedule) will allow you to select  screen  or 
printer output,  and further to select printer type and carriage length. If 
you  select option 3 you will be asked the same question;  it will  compute 
the path if data is present,  otherwise it will put the program into a mode 
to accept new data (option 0). 
 
Options 4 and 5 are to save and retrieve data from cassette. I haven't used 
them for some time and dont know whether they are still working.

Option  8  will allow you to print a bar chart from the  computed  critical 
path information.

Option 9 quits the program (and also overwrites it).









Ron Clark

MicroBee Users Group 
of South Australia

April 1987
his  example  is 
contained in file TENT.DAT or TENT1.DAT. It can be loaded using option 7.

Two  data  f